## Page 1
ID | Topic |  | Differences between the 4th and 5th editions | IPMA Project Management |  |  |  |  | IPMA PMO |  |  |  | Explanation of differences (column D)
|  |  |  | B | C | D | Learning Outcomes |  | B | C | D | Learning Outcomes
Technical Competencies | [14 empty] | Taxonomy
3.00 | Project orientation | [13 empty] | b = Understanding |  | t = Applying |  | a = Analyze
| What is a project? |  |  | a | t | b | C21a |  | a | t | t | C21b |  |  | Verbs | Nouns | Verbs | Nouns | Verbs | Nouns
| What is project management? |  |  | a | t | b | C21b |  | a | t | t | C21b
| Reasons to Start a Project |  |  | a | a | t | C21f |  | a | t | b | C21c |  |  | Recognize | Terms | Apply | Situations | Analyze | Analyses
| Projects in Organizations |  |  | a | t | b | C21c |  | a | t | t | C21b | Included separately; in the 4th edition, this was part of “Project Characteristics” |  | Identify | Facts | Drafting | Applications | Derive | Models
| Characteristics of a project |  |  | a | a | t | C21e |  | a | t | t | C21b |  |  | Compare | Processes | Implement | Principles | Evaluate | Problems
| Conditions of a project |  |  | a | a | t | C21e |  | a | t | t | C21b |  |  | Describe | Relationships | Calculate | Criteria | Design | Conclusions
| Work Methods |  |  | a | a | b | C21d |  | t | t | b | C21a |  |  | Define | Standards | Define | Rules | Prioritizing | Predictions
| Phasing, managing, and decision-making |  |  | a | t | b | C21h |  | b | b | b | C21e |  |  | Explain | Rules | Choosing | Methods | Relate | Comment
| Triple Constraint |  |  | t | t | t | V11a |  | t | t | t | V11a |  |  | Reproduce | Criteria | Solve | Conclusions | Conclude | Concepts
| Projects within the product lifecycle |  |  | b | b | b | C21g |  | b | b | b | C21d
| Projects at Different Levels |  |  | a | t | b | C21i |  | a | t | t | C21b
| Project results, outcomes, benefits, and objectives |  |  | b | b | b | V21a |  | t | t | t | V21a |  |  | Legend
| Project Excellence Baseline (in-depth) | [7 empty] | b |  |  | C21f |  |  |  | Competency Areas (Technical, Behavioral, and Context) IPMA Textbook
Sections (4–11) of the IPMA textbook
4.00 | Project preparation | [14 empty] | Chapters in the IPMA Textbook
4.01 | Project preparation phase
| Project preparation phase |  |  | t | t | b | V101a |  | t | t | t | V101a |  |  |  | In the Advanced section of the IPMA textbook (Column B)
| Project mandate and project proposal |  |  | t | t | b | V101a |  | t | t | t | V101a |  |  |  | Section in Project Management based on ICB Version 4 (Column C)
| Project Assignment |  |  | t | t | b | V101b |  | t | t | b | V101b |  |  |  | Subsection in Project Management based on ICB Version 4 (Column D)
| Project Definition Phase Plan |  |  | t | t | b | V101a |  | t | t | t | V101a |  |  |  | Topic added in the Dutch version compared to the English version (columns C and D)
| Project Decision |  |  | t | t | b | V101c |  | t | t | b | V101c |  |  |  | Topic missing compared to the Dutch IPMA PMO learning outcomes (columns C and D)
4.02 | Stakeholders | [14 empty] | Text content updated from Edition 4 to Edition 5 (Column E)
| Stakeholder Management |  |  | t | t | b | V121b | 1 | t | t | b | V121b |  |  |  | New topic in the 5th edition compared to the 4th edition (column E)
| Stakeholder Analysis |  |  | a | t | t | V121a | 2 | t | t | t | V121a |  |  |  | Topic not included in the 5th edition (column E)
| Stakeholder Management Strategy |  |  | t | t | b | V121b | 3 | t | t | b | V121b | Various approaches added
| Communication Plan |  |  | t | t | b | V121b | 4 | t | t | b | V121b |  |  |  | No learning outcome for the relevant level (columns F–I and K–N)
| Stakeholder Engagement |  |  | a | t | b | V121c | 5 | a | t | t | V121c |  |  |  | Learning outcomes not explicitly listed but still relevant (columns F–I and K–N)
| Managing Expectations |  |  | a | t | b | V121c | 6 | a | t | t | V121c |  |  |  | Not part of the Dutch learning outcomes (columns F–H and K–M)
4.03 | Project Organization
| Project Governance |  |  | a | t | b | V51a | [5 empty] | Added; replaced “project management” with “project organization” |  | Certification Levels
| Principles of Project Organization |  |  | b | b | b | V51b |  | b | b | b | V51a |  |  | B | IPMA-B
|  | > Separation of engineering and management |  | b | b | b | V51c |  | b | b | b | V51b |  |  | C | IPMA-C
| Project Management Structure |  |  | a | t | b | V51d |  | a | t | t | V51c |  |  | D | IPMA-D
| Project Organization |  |  | a | t | b | V51d |  | a | t | t | V51c | "Project Management" and "Various Client Roles" have been removed
| Roles and Responsibilities |  |  | a | t | b | V51e |  | a | t | t | V51d | The “Change Authority” as a separate role has been removed > now fully integrated into Chapter 6.03
| Consultation Structure and the Linking-Pin Principle |  |  | a | t | b | V51f |  | t | t | t | V51e |  |  | Addendum NL
| Responsibility Matrix |  |  | a | t | b | V51g |  | t | t | t | V51f | RASCI instead of RACI |  | Chapter | Topic |  |  | PMO
[15 empty] | 5.02 | Project Success Factors According to Standish |  |  | V11b
4.04 | Requirements and Objectives | [13 empty] | 5.03 | Control points and planning packages |  |  | V32c
| Project Results, Objectives, Outcomes, Benefits, and Goals |  |  | a | t | b | V21a |  | t | t | t | V21a | Expanded to include the concepts of “outcome” and “benefits” + explanation of SMART objectives |  | 5.07 | Obligation Tracking |  |  | V72f
| Expectations, requirements, and acceptance criteria |  |  | a | t | b | V21d |  | t | t | t | V21d |  |  | 6.05 | Color-Coded Thinking |  |  | V131d
| Quality Requirements and Specifications |  |  | a | t | b | V21e |  | t | t | b | V21e |  |  | 9.04 | Setting up a permanent PMO |  |  | C24b
|  | > Fit-for-use and fit-for-purpose |  | a | t | b | V21f |  | b | b | b | V21f |  |  | 9.04 | PM standards |  |  | C26a
| Value Management (in-depth) |  |  | t | b |  | V21b |  | t | b |  | V21b
| Total Cost of Ownership (in-depth) |  |  | b | b |  | V21c |  | t | b |  | V21c |  |  | Compared to the English handbook, the Dutch handbook includes a few additional topics.
| Product Cost Management (Advanced) | [11 empty] | New, taken from the EN edition; no Dutch learning outcome |  | The Dutch handbook thus covers all learning outcomes for the IPMA PM certification in the Netherlands.
However, some topics are missing from the IPMA PMO certification. Therefore, they are provided in a separate addendum.
4.05 | Risks and Opportunities
| Risks and Opportunities |  |  | a | t | b | V111c | 1 | b | b | b | V111a
|  | > Probability, impact, and horizon |  | t | t | b | V111g | 2 | b | b | b | V111e
|  | > Difference Between Risks and Issues |  | a | t | b | V111c | 3 | b | b | b | V111a
|  | > Difference between risks and uncertainties in estimates |  | a | t | b | V111c | 4 | b | b | b | V111b
| Various risk concepts |  |  | b | b | b | V111d | 5 | b | b | b | V111c | Added: Risk Capacity
| Risk Management |  |  | t | t | t | V111b | 6 |  |  |  |  | Added: Simplified version of risk management processes
| Risk Management Strategy |  |  | a | t | b | V111a | 7 |  |  |  |  | New, adopted from the EN edition
| Risk owner and risk action owner |  |  | t | t | b | V111e |  | b | b | b | V111d | Definition of “Risk Action Owner” updated
| Types of Risks |  |  | t | b |  | V111h |  | t | t | b | V111f | Risk categories are now referred to as “types of risks.” Risk categories now include a risk checklist
| Risk Categories |  |  | t | t | b | V111i
| Risk Mitigation Measures |  |  | t | t | t | V112b |  | t | t | t | V112b
| Inherent, residual, and secondary risk |  |  | b | b | b | V112d |  | t | t | b | V112d
| Risk techniques, risk register |  |  | t | t | b | V113a |  | a | t | t | V113a
| Risk budget and contingency reserve |  |  | a | t | b | V113d |  | a | t | b | V71d | Definitions updated
| Probability Measures (Advanced) |  |  | t | t |  | V112c |  | b | b |  | V112c
| ISO 31000:2018: Risk Management (Advanced) |  |  | t | t |  | V112a |  | a | t | b | V112a | ISO 31000 principles updated
| Risk Identification Techniques (Advanced) |  |  | t | t |  | V113b |  | a | t | b | v113b | Added: External Environment Scan
| Risk Analysis Techniques (Advanced) |  |  | t | b |  | V113c |  | t | t | b | V113c
5.00 | Project Definition
5.01 | Project Definition Phase
| Activities in the project definition phase |  |  | a | t | b | V102b |  | t | t | t | V102b
| Project Management Plan |  |  | a | t | b | V102b |  | t | t | t | V102b
| Project Start-up |  |  | a | t | b | V102a |  | a | t | t | V102a | Two PSU variants included
| Kick-off |  |  | a | t | b | V102a |  | a | t | t | V102a
| Project evaluation and decision |  |  | a | t | b | V102d |  | t | t | t | V102d
| Setting Up Project Support (Advanced) |  |  | t | t |  | V102c |  | a | t | t | V102c | Removed: Step-by-step plan for setting up project support
5.02 | Project Design
| Project Approach and Project Design |  |  | t | t | b | V11b |  | t | b | b | V11b | Added: Project Design
| Project Success |  |  | t | t | b | V11c |  | t | t | t | V11a
| Project Success Criteria |  |  | t | t | t | V11a |  | t | t | t | V11a
| Project Success Factors |  |  | t | t | b | V11b | [5 empty] | New, adopted from the EN edition
|  | > Success Factors According to the Standish Group | [6 empty] | t | t | b | V11b | Discontinued: Success factors according to the Standish Group; however, there is a learning outcome for IPMA PMO
| Project Management Success |  |  | t | t | b | V11c |  | t | b | b | V11c
| Lessons Learned |  |  | t | t | b | V11e | 1 | t | t | t | V11d
| Diamond Model (Advanced) | [6 empty] | 2 | t | b | b | V11e
| Project Performance Management (Advanced) |  |  | t | b |  | V11d | 3 |  |  |  |  | New, adopted from the EN edition
5.03 | Scope
| Scope |  |  | a | t | b | V31a |  | t | t | t | V31a | Added: Interfaces
| Scope Creep and Scope Changes |  |  | a | t | b | V31b |  | t | t | t | V31b
| Project Decomposition |  |  | a | t | b | V32a |  | t | t | t | V32a
| Work Breakdown Structure (WBS) |  |  | a | t | b | V32b |  | t | t | t | V32a
|  | Control points and planning packages | [6 empty] | t | t | t | V32c | Removed: Control Points and Planning Packages; however, there is a learning outcome for IPMA PMO
| Product Breakdown Structure (PBS) |  |  | a | t | b | V32c |  | t | t | t | V32a
|  | > Product flowchart, swimlanes |  | a | t | b | V32c |  | t | t | t | V32b
| Scope (Configuration) Management | [11 empty] | New, adopted from the EN edition
| Position of Subprojects in a WBS (Advanced) | [11 empty] | New, adopted from the EN edition
5.04 | Quality
| Process and Product Quality |  |  | b | b | b | V61a |  | b | b | b | V61a
| Standard operating procedures |  |  | b | b |  | V61b | [5 empty] | New, adopted from the EN edition
| Verification and validation |  |  | t | t | b | V61c |  | t | t | t | V61b
| Quality Management |  |  | t | t | b | V61d |  | t | t | b | V61c
| Quality Management Strategy and Plan |  |  | a | t | b | V61e | [5 empty] | Content updated
| Deming Cycle |  |  | t | t | t | V104g |  | t | t | t | V104d
| Standards, norms, and regulations |  |  | t | t | b | C32f |  | b | b | b | C32g
| Quality review, audit, and evaluation |  |  | t | t | b | V62a |  | t | t | b | V62a
| Quality Register/Test Register |  |  | t | t | b | V62d |  | a | t | t | V62d
| Quality Tools |  |  | a | t | b | V61f |  | t | t | t | V61d
| Additional Quality Tools (Advanced) |  |  | a | t |  | V61g |  | t | t | t | V61d
| Inspection Methods and Techniques (Advanced) |  |  | t | b |  | V62b |  | b | b |  | V62b
| Test Concepts and Methods (Advanced) |  |  | t | b |  | V62c |  | b | b | b | V62c | Added: Automated testing
| Quality Costs (Advanced) | [7 empty] | b | b |  | V61e
5.05 | Time
| Planning levels |  |  | t | t | b | V41a | [5 empty] | New, adopted from the EN edition
| Baselines |  |  | a | t | b | V41b |  | a | t | t | V33d | Added separately as a supplement to 6.02 configuration baselines
| Milestones, Phases, and Decision Points |  |  | t | t | b | V41f |  | a | t | b | V41d | Figure: Phasing in Practice (deleted)
| Phasing Models |  |  | t | t | b | V41g |  | a | t | b | V41e | Figure: Phasing Models Updated
| Planning Techniques | [7 empty] | a | t | t | V41a | New, included as an introduction to the following learning outcomes
| Precedence chart |  |  | t | t |  | V41d |  | a | t | t | V41b
| Gantt chart |  |  | t | t | t | V41c |  | a | t | t | V41a
| Shortening the Timeline |  |  | t | t | b | V41h |  | t | t | t | V41f
| Other planning constraints (in-depth) |  |  | a | b |  | V41e |  | b | b |  | V41c | Added: Expanded Activity Block
| Three-point estimates (in-depth) |  |  | a | t |  | V103c |  | a | t |  | V103c
5.06 | People and Resources
| Capacity Management |  |  | t | t | b | V81a |  | a | t | t | V81a
| Gross-Net Capacity |  |  | a | t | b | V103a |  | a | t | t | V103a
| Capacity Plan |  |  | t | t | b | V81c |  | a | t | t | V81c
|  | > Leveling and smoothing |  | t | t | b | V81b |  | a | t | t | V81b | Smoothing added, definitions updated
| Estimation methods and techniques |  |  | a | t | b | V103b |  | a | t | b | V103b | Structure revised
| Critical Chain Method (in-depth) |  |  | t | b |  | V81d |  | b | b |  | V81d
5.07 | Finance
| Estimating, Budgeting, and Monitoring |  |  | t | t | t | V72c |  | a | t | t | V72c
| Cost Breakdown |  |  | t | t | t | V71a |  | a | t | t | V71a
| Reserves |  |  | t | b | b | V71c |  | a | t | b | V71d
| Cost and Budget Monitoring |  |  | a | t | t | V72e |  | a | t | t | V72e | New, included as an introduction to the following learning outcomes
| Reporting Standards |  |  | t | t | t | V72d |  | a | t | t | V72d
| Obligation Tracking | [7 empty] | a | t | b | V72f | Final term for IPMA PMO
| Alignment of project and general accounting |  |  | t | b | b | V72b |  | a | t | t | V72b | Structure revised
| Power of attorney and proxy |  |  | t | b | b | V72a |  | a | t | t | V72a | Added: Power of attorney
| Linking CBS with WBS and OBS (advanced) |  |  | t | t | t | V71b |  | t | t | t | V71b
|  | > Responsibility Assignment Matrix |  | t | t | t | V71b |  | t | b |  | V71c
|  | > Control points |  | t | t | t | V71b |  | t | t | t | V32c | Added: Control points (removed from Section 5.03)
| Liquidity Planning (Advanced) |  |  | t | b |  | V73b |  | t | b | b | V73b
| Project Financing (Advanced) |  |  | b |  |  | V73a |  | t | b |  | V73a
5.08 | Business Justification
| Characteristics of a business case |  |  | a | t | b | C14a |  | a | t | b | C14a
| Business case document |  |  | a | t | b | C14a |  | a | t | b | C14a
| Baseline measurement, baseline and base scenarios, and delta measurement |  |  | a | t | b | C14b |  | b | b | b | C14b | Baseline measurement and baseline and base scenarios have been separated
| Business case in the product life cycle |  |  | a | t | b | C14d |  | t | t | b | C14d | Topic further elaborated
|  | > Feasibility study, benefits review, post-investment assessment |  | a | t | b | C14e |  | t | t | b | C14e | Benefits Review and Post-Investment Assessment split
| Client and contractor business cases |  |  | a | t | b | C14c |  | b | b | b | C14c
6.00 | Project implementation and closure
6.01 | Procurement
| Make or buy |  |  | t | t | b | V91a |  | a | t | b | V91a | Breakdown of in-house vs. outsourced has been removed
| Procurement process |  |  | t | b | b | V91c |  | a | t | b | V91c
| Selection and Award Criteria |  |  | t | b | b | V91c |  | a | t | b | V91c
| Best-Efforts and Results-Based Obligations |  |  | t | t | b | V92c |  | b | b | b | V92c
| Standard Contract Clauses |  |  | t | t | b | V92b |  | t | t | b | V92b
| General Terms and Conditions |  |  | t | t | b | V92b |  | t | t | b | V92b | Alternative “Last Shot” added
| Responsibilities |  |  | t | b | b | V91c |  | t | b | b | V91c
| Organizational Procurement Strategy (Advanced) | [11 empty] | New, taken from the EN edition; no NL final term
| Supplier Development (Advanced) | [11 empty] | New, taken from the EN edition; no NL final term
| Procurement Strategy and Plan (Advanced) |  |  | t | b |  | V91b |  | t | b |  | V91b
| Types of Contracts (in-depth) |  |  | t | b |  | V92a |  | b | b | b | V92a | Co-creation as a contract type has been removed; now listed under partnerships
| RFI, RFS, RFP, RFQ (Advanced) |  |  | t | b |  | V91d |  | t | b | b | V91d | RFS added
| Concept of Supply and Demand (Advanced) | [11 empty] | New, taken from the EN edition; no Dutch learning outcome
| Bidding Procedures (Advanced) |  |  | t | b |  | V91h
| Pre-Contractual Agreements (Advanced) |  |  | t | b |  | V91e |  | t | t | b | V91e | Broken down into letter of intent, preliminary agreement, and early implementation agreement
| Financial Guarantees (Advanced) |  |  | t | b |  | V92d |  | b | b |  | V92d | Divided into bank guarantees, letters of credit, and export credit guarantees
| European procurement (in-depth) |  |  | a | t | b | V91g |  | b | b |  | V91g | 5 instead of 4 procurement options
| Contract Management (Advanced) |  |  | t | b |  | V92e |  | t | t | b | V92e
| Claims Management (Advanced) |  |  | t | b |  | V92f |  | b | b |  | V92f
| Partnerships (Advanced) |  |  | b |  |  | V91f |  | b | b |  | V91f | Added: Joint venture
| Supply Chain Management (Advanced) |  |  | t | b |  | C25d |  | b |  |  | C25d | Originally appeared in 10.01
6.02 | Change Management
| Change Management vs. Change Leadership |  |  | b | b | b | V105a | [5 empty] | New: Explanation of the terms to be used
| Changes and Project Issues |  |  | t | t | t | V105b |  | t | t | t | V105a
| Change Strategy and Procedure |  |  | t | t | t | V105c |  | a | t | t | V105b
| Deviations from Specifications |  |  | t | t | t | V105b |  | a | t | t | V105b | Explanatory notes updated
| Other Project Issues |  |  | t | t | t | V105b |  | a | t | t | V105b
| Issue Register |  |  | t | t | t | V105c |  | a | t | t | V105b
| Change Authority |  |  | t | t | b | V105d |  | a | t | b | V105c
| Change Budget |  |  | t | t | b | V105d |  | a | t | b | V105c
| Priority and urgency |  |  | t | t | t | V105e |  | a | t | b | V105d
| Configuration Management (Advanced) |  |  | t | b |  | V33a |  | t | t | t | V33a
|  | > CI Record and CMDB |  | t | b |  | V33b |  | t | t | t | V33b
|  | > Configuration management strategy and plan |  | t | b |  | V33c |  | a | t | b | V33c | Added: Configuration Management Strategy
|  | > Configuration management baseline and product status overview |  | t | b |  | V33d |  | t | t | t | V33d
|  | > Change management and configuration management |  | t | b |  | V33a |  | a | t | b | V105e
6.03 | Information and Documentation
| Information vs. Data |  |  | b | b | b | V52b |  | b | b | b | V52a
| Information and Document Management |  |  | t | t | b | V52c |  | a | t | t | V52b
| Information Management Strategy |  |  | a | t | b | V52a | 1 |  |  |  |  | New, adopted from the EN edition
| Information Management Plan |  |  | t | t | b | V52f | 2 | a | t | t | V52d
| Information Management Infrastructure |  |  | t | t | b | V52d | 3 |  |  |  |  | New, adopted from the EN edition
| Quality and Security Requirements |  |  | b | b | b | V52g |  | a | t | t | V52e
| Project File Structure |  |  | t | t | b | V52h |  | a | t | t | V52f
| I/O matrix |  |  | t | b |  | V52e |  | t | t | t | V52c
| Information Management Techniques (Advanced) | [11 empty] | New, taken from the EN edition; no Dutch learning outcome
6.04 | Control and Reporting
| Management Cycle |  |  | t | t | t | V104g |  | t | t | t | V104d
| Management and Reporting Levels |  |  | t | t | t | V104h |  | t | t | t | V104e
| Management by Objectives |  |  | a | t | b | V104a |  | b | b | b | V104a
| Management by Exception |  |  | a | t | b | V104b |  | t | t | b | V104b
| Day-to-day management |  |  | a | t | b | V104c |  | t | t | b | V104c | Explanatory notes updated
| Managing Phase Transitions |  |  | t | t | t | V104d |  | t | t | b | V104c
| Escalating Deviations |  |  | a | t | b | V104e |  | t | t | b | V104c
| Project Control |  |  | t | t | b | V104f |  | t | t | b | V104c
| Project management products |  |  | t | t | b | V104f |  | t | t | b | V104c | New, included as an introduction to the following learning outcomes
|  | > Management reports |  | a | t | b | V104k |  | a | t | t | V104h
| Trend Analyses |  |  | a | a | t | V104j |  | t | t | t | V104f
| Earned Value Analysis (Advanced) |  |  | a | t |  | V104i |  | a | t |  | V104f
6.05 | Change and Transformation
| Change Management |  |  | t | b | b | V131a | [5 empty] | New, adopted from the EN edition
| Change Management Approach |  |  | t | b | b | V131b | [5 empty] | New, adopted from the EN edition
| Leadership in Change – Kotter |  |  | t | b |  | V131c |  | b | b |  | V131a | Structure and explanatory notes updated
| Kübler-Ross Stages of Grief (Advanced) | [11 empty] | New, taken from the EN edition; no Dutch learning outcome
| Diffusion of Innovations – Rogers (Advanced) |  |  | t | b |  | V131d |  | b |  |  | V131b
| Learning Organizations – Senge (Advanced) |  |  | t | b |  | V131e |  | b | b | b | V131c
| Transformational Learning – Schein (Advanced) | [7 empty] | t | t | b | V131d | Explanatory notes updated
| Change Paradigms - De Caluwé/Vermaak |  |  | t
| De Caluwé’s Color-Based Thinking (in-depth) | [7 empty] | t | t | b | V131d | DeCaluwé’s “Color-Coded Thinking has been discontinued; however, it remains a learning outcome for the IPMA PMO
6.06 | Project Closure
| Delivery and Handover of Project Results |  |  | t | t | b | V106a |  | t | t | t | V106a
| Winding Down the Project |  |  | t | t | b | V106b |  | t | t | t | V106c
| Evaluation |  |  | t | t | b | V106c | 1 | t | t | t | V106b
| Dissolving the Project Team |  |  | t | t | b | V106b | 2 | t | t | t | V106c
| Closure and Discharge |  |  | t | t | b | V106d |  | t | t | t | V106d
Behavioral Competencies
7.00 | Self-Management
7.01 | Self-Reflection and Self-Management
| Self-Reflection and Self-Analysis | [11 empty] | New, included as an introduction to the following learning outcomes
| Emotional Intelligence |  |  | t | b | b | G11a |  | t | b | b | G11a
| Johari Window |  |  | t | t | b | G11c |  | t | t | t | G11c
| Big Five personality theory | [11 empty] | Content adapted but no longer includes the Dutch learning objective
| Core Quadrants |  |  | a | t | b | G11d |  | t | t | b | G11d
| Personal Effectiveness | [11 empty] | New, included as an introduction to the following learning outcomes
| Self-Motivation |  |  | b | b | b | G12a |  | b | b | b | G12a
| The Seven Habits of Highly Effective Leaders |  |  | t | b |  | G12c |  | t | b | b | G12c
| Personal Time Management |  |  | t | t | t | G12d |  | a | t | t | G12d
| Stress Management |  |  | b | b | b | G13a |  | b | b | b | G13a | New, included as an introduction to the following learning outcomes
| Tension versus Stress (Eustress and Distress) |  |  | b | b | b | G13a |  | b | b | b | G13a | Eustress and distress are new concepts
| Triggers and symptoms of stress |  |  | b | b | b | G13b |  | b | b | b | G13b | Job Demand and Control model added, no Dutch learning outcome
| Stress Reduction Techniques |  |  | b | b | b | G13c |  | b |  |  | G13c
| Rational Emotive Therapy (in-depth) |  |  | b | b |  | G11b | 1 | b |  |  | G11b
| Personal Time Management Techniques (in-depth) |  |  | t | b |  | G12e | 2 |  |  |  |  | New, adapted from the EN book
| Steps in Goal Setting (Advanced) |  |  | b | b |  | G12b |  | t | b |  | G12b
| Intervention Techniques for Reducing Stress (in-depth) |  |  | b | b |  | G13d |  | b | b |  | G13d
7.02 | Personal Integrity and Reliability
| Aspects of Reliability |  |  | b | b | b | G22a |  | b | b | b | G22a
| Types of Ethics |  |  | t | b | b | G21a |  | t | b | b | G21a
| Principles of Social Justice and Sustainability |  |  | t | b |  | G21b | [5 empty] | New, adapted from the EN book
| Professional Standards and the IPMA Code of Conduct | [6 empty] | 1 | b | b | b | G21c
| Ethics Test (Advanced) |  |  | b | b |  | G21c | 2 | b | b |  | G21b
| Personal Ethics vs. Business Ethics (Advanced) |  |  | b | b |  | G21c | 3 | b | b |  | G21b
| UN Universal Declaration of Human Rights (in-depth) |  |  | b | b |  | G22c
7.03 | Personal Communication
| Communication, communication model |  |  | b | b | b | G31a |  | b | b | b | G31a
|  | > Criteria for effective communication |  | a | a | t | G31e |  | a | t | t | G31e
|  | > Communication channels |  | b | b | b | G31c |  | a | t | b | G31c
|  | > Verbal and nonverbal communication |  | t | t | t | G32a |  | t | t | t | G32a
|  | > Miscommunication and noise |  | a | t | b | G31d |  | a | t | b | G31d
| Aspects of Communication |  |  | a | t | b | G31b |  | t | t | b | G31b
| Active Listening |  |  | t | t | t | G32b |  | t | t | t | G32b
| Asking the Right Questions |  |  | t | t | t | G32c |  | t | t | t | G32c
| Giving and Receiving Feedback |  |  | a | t | t | G32d |  | t | t | b | G32d
| Meetings |  |  | a | t | b | G33a |  | a | t | b | G33a
|  | > Agenda and agenda items |  | a | t | b | G33b |  | t | t | b | G33b
|  | > Roles and Responsibilities in Meetings |  | a | t | b | G33c |  | t | t | t | G33c
| Facilitated workshops |  |  | b | b | b | G34a |  | t | t | b | G34a
|  | > Organizing and conducting workshops |  | a | t | b | G34b |  | a | t | t | G34b
|  | > Applicable working methods |  | a | t | b | G34b |  | t | t | t | G34b | Applicable working methods added
|  | > Workshops on roles and responsibilities |  | a | t | b | G34c |  | t | b | b | G34c
| Written communication |  |  | a | t | b | G36a |  | t | t | t | G36a
|  | > Document design and structure |  | a | t | b | G36b |  | t | t | b | G36b
| Presentations |  |  | a | t | b | G35a |  | a | t | b | G35a
|  | > Visual aids |  | a | t | b | G35c |  | a | t | b | G35c | Explanation shortened
| Elevator pitch (in-depth) |  |  | t | t |  | G35b |  | b | b |  | G35b | Structure refined (5P structure)
| Delivering Bad News (Advanced) |  |  | t |  |  | G32e |  | t |  |  | G32e
8.00 | Connecting with Others
8.01 | Relationships and Engagement
| Aspects, characteristics, and policies regarding openness |  |  | a | t | b | G41b |  | t | t | b | G41b
| Building Arguments | [7 empty] | t | t | b | G42b
| Building Networks |  |  | t | b |  | G22b |  | a | b | b | G22b | Incorrectly marked in the book
| Motivation Theories | [11 empty] | New, included as an introduction to the following learning outcomes | [7 empty] | g
| Maslow’s Hierarchy of Needs |  |  | t | t | b | G43b | [5 empty] | New, taken from the EN book / new learning outcome for IPMA PM
| Motivation and Hygiene Factors |  |  | t | b |  | G43a |  | t | b | b | G43b
| Theory X and Theory Y managers | [11 empty] | New, adapted from the EN book; no NL learning outcome
| Creating an Open Corporate Culture (Advanced) |  |  | b |  |  | G41a | 1 | t | b |  | G41a
| Behavioral Patterns/Leary’s Rose (in-depth) |  |  | t | b |  | G42b | 2 | a | t | b | G42c
| The Project Manager as an Advisor (in-depth) |  |  | a | t |  | G42a | 3 | t | b |  | G42a | Principles further elaborated
| Self-Determination Theory (in-depth) | [6 empty] | 4 | t | b |  | G43a
| Spiral Dynamics (in-depth) | [6 empty] | 5 | t | b |  | G11e | New, taken from the English book; no learning outcome for PM
8.02 | Leadership
| Differences Between Leadership and Management |  |  | b | b | b | G51a |  | b | b | b | G51a
| Leadership Styles |  |  | t | t |  | G51d |  | t | b |  | G51d
| Contingency theory | [11 empty] | New, adapted from the EN book; no NL learning outcome
| Situational Leadership |  |  | t | t | b | G51c |  | a | t | b | G51c
| Circles of Influence and Engagement |  |  | t | t | b | G51e |  | t | b | b | G51e
| Levels of Assertiveness |  |  | t | t | b | G51f |  | t | t | b | G51f
| Role content, interpretation, and expectations (in-depth) |  |  | t | b |  | G51g |  | t | b |  | G51g
| Coaching (in-depth) |  |  | t |  |  | G51h | [5 empty] | New, in-depth coverage of the coaching leadership style
| Servant leadership (in-depth) |  |  | t |  |  | G51i | [5 empty] | New, taken from the EN book; learning outcome B level
| Meaning and Purpose (Advanced) | [11 empty] | New, adapted from the EN book; no NL learning outcome
| Three Levels of Leadership (Advanced) |  |  | a | b |  | G51b |  | a | b |  | G51b
| Vroom and Yetton Decision-Making Model (Advanced) |  |  | t |  |  | G51j | [5 empty] | New, taken from the EN book; learning outcome B level
8.03 | Teamwork
| Teams and Team Development Stages |  |  | t | t | t | G61a |  | a | b | b | G61a
| Situational Leadership and Team Development |  |  | t | t | b | G61b |  | a | b | b | G61b
| Interventions During Team Phase Transitions |  |  | t | t | b | G61b |  | a | b | b | G61b
| Team Building |  |  | t | t | t | G61a |  | a | b | b | G61a
| Dealing with Resistance |  |  | t | t | b | G62c |  | t | b | b | G62c | Content updated
| Team Composition (Advanced) |  |  | t | t |  | G62a |  | t | t |  | G62a
| Developing an Effective Project Culture (Advanced) |  |  | t | b |  | G62f | [5 empty] | New, adapted from the EN book
| Team Roles (in-depth) |  |  | t | b |  | G62b |  | b | b |  | G62b | Roles shortened; project types redefined
| Groupthink (in-depth) |  |  | t | b |  | G62d |  | b |  |  | G62d
| Dealing with Resistance (Supplementary, In-Depth) |  |  | t | t |  | G62c |  | t |  |  | G62c | In-depth discussion of resistance; no Dutch learning outcome
| Remote Teams (Advanced) |  |  | t | b |  | G62e |  | t | t | b | G62e
8.04 | Resourcefulness
| Thinking Methods | [11 empty] | New, adapted from an English book; no Dutch learning outcome
| Analytical Problem Solving |  |  | t | t | b | G81e | [5 empty] | New, taken from the EN book / new learning outcome for IPMA PM
| Creative Problem Solving |  |  | t | t | b | G82a |  | t | t | b | G82a
| Decision-making methods |  |  | t | t | b | G81d |  | t | b | b | G81e
| Cause Identification and Analysis Techniques |  |  | t | b |  | G81a |  | t | b | b | G81b
| Solution identification and analysis techniques |  |  | t | b |  | G81b |  | t | b | b | G81c
| Solution assessment and evaluation techniques |  |  | t | b |  | G81c | 1 | t | b |  | G81d
| Divergent creativity techniques |  |  | t | t | b | G82b | 2 | t | t | b | G82b
| Convergent creativity techniques |  |  | t | t | b | G82d | 3 | t | t | b | G82d
| Problem-Solving in Standardized Processes (Advanced) | [7 empty] | b | b |  | G81a
| Additional Divergent Creativity Techniques (Advanced) |  |  | b |  |  | G82c |  | t | b |  | G82c
| Additional Convergent Creativity Techniques (Advanced) |  |  | b |  |  | G82e |  | t | t |  | G82e
| Structured Decision-Making Process (Advanced) |  |  | b |  |  | G82f | [5 empty] | New, taken from the EN book; learning outcome B
| Validating Products in Innovative Processes (Advanced) | [11 empty] | New, taken from the English book; no Dutch learning outcome
| Implementation of Organizational Innovation (Advanced) | [11 empty] | New, taken from the English book; no Dutch learning outcome
8.05 | Results-Orientation
| Efficiency, Effectiveness, and Productivity |  |  | b | b | b | G101a |  | t | b | b | G101a
| Continuous improvement (kaizen) |  |  | b | b |  | G101c |  | a | t | b | G101d
| Techniques for improving efficiency (advanced) |  |  | b | b |  | G101d | 1 | t | b | b | G101e
|  | > 4M checklist |  | b | b |  | G101d | 2 | t | b |  | G101f | For the 7 statistical tools, see Chapter 5.04 (V61d)
| Results-oriented project management (advanced) | [6 empty] | 3 | t | b |  | G101b
| Political and Social Sensitivity (Advanced) |  |  | t | b |  | G101e | 4 | t | b |  | G101g
| Entrepreneurship (Advanced) |  |  | b |  |  | G101b | 5 | t | b |  | G101c
8.06 | Negotiation
| Negotiation strategies |  |  | t | t | b | G91a |  | a | t | b | G91a
| Positional negotiation |  |  | t | t | b | G91c |  | a | t | b | G91c
| Principled Negotiation – The Harvard Method |  |  | t | t | b | G91b |  | a | t | b | G91b
| Best Alternative Without a Contract (BAZO) |  |  | t | t | b | G91b |  | a | t | b | G91b
| Phases in a Negotiation Process (Advanced) |  |  | t | t |  | G91d |  | t | b |  | G91d
| Aspects of Influence in Negotiations (Advanced) |  |  | t | b |  | G91e |  | t | b |  | G91e
| Negotiation Tactics (Advanced) | [11 empty] | New, taken from the English book; no Dutch learning outcome
8.07 | Conflicts and Crises
| Functional and Dysfunctional Conflicts |  |  | b | b | b | G72b |  | b | b | b | G72a
| Types of Conflicts |  |  | b | b |  | G72a |  | b | b | b | G72a
| Conflict Management Styles |  |  | t | t | b | G72e |  | a | t | b | G72d
| Stages of Conflict |  |  | t | t | b | G72c |  | b | b | b | G72b
| De-escalation in Different Stages of Conflict |  |  | a | t | b | G72d |  | t | b | b | G72c
| Different Roles in Conflicts (Advanced) |  |  | t | t |  | G72f |  | t | b |  | G72e
| Crises and Crisis Management (Advanced) |  |  | t | b |  | G71b |  | t | b |  | G71b | Addition of the emergence of crises within projects
| Crisis Plan (Advanced) |  |  | t |  |  | G71a |  | t | b |  | G71a | Worst-case scenario added
Contextual Competencies
9.00 | Implementing Change
9.01 | Strategy
| Company Mission, Vision, and Core Values |  |  | b | b | b | C11a |  | a | t | b | C11a
|  | > Core values |  | b | b | b | C11b |  | a | t | b | C11b
| Strategy and Strategic Goals |  |  | b | b | b | C11f | [5 empty] | Tactics and strategy added
| Benchmarking |  |  | a | t | b | C12c |  | t | b | b | C12d
| SWOT Analysis |  |  | a | t | b | C11e |  | a | t | b | C11e | Added a comparison matrix
| 10 Ways to Develop Strategies (in-depth) | [11 empty] | New, taken from the English book; no Dutch learning outcome
| Business Model Canvas (in-depth) |  |  | b | b |  | C11d |  | t |  |  | C11d
| McKinsey 7S Model (in-depth) |  |  | b |  |  | C11c |  | b |  |  | C11c
| Strategic Performance Management (Advanced) |  |  | t | b |  | C12b |  | t | b |  | C12b
| EFQM Model (Advanced) | [7 empty] | b |  |  | C12c | Updated to reflect the 2021 update
| Investment Calculations (Advanced) | [11 empty] | New, included as an introduction to the following learning outcomes
| Return on Investment (Advanced) |  |  | a | t | b | C13a | [5 empty] | New, adapted from the EN book
| Profitability Ratios (Advanced) | [11 empty] | New, taken from the English book; no Dutch learning outcome
| Net Present Value (Advanced) |  |  | a | t |  | C13b |  | a | t |  | C13a | The current year is year 0 instead of year 1; formulas adjusted accordingly
| Payback period (in-depth) |  |  | a | t |  | C13c |  | a | t |  | C13b
| Break-even point (in-depth) |  |  | a | t |  | C13c |  | a | t |  | C13b
9.02 | Program Management
| Programs and Program Management |  |  | t | b |  | C22a |  | b | b | b | C22b
| Differences Between Projects and Programs |  |  | t | b
| Differences between projects and programs |  |  | t | b |  | C22c |  | b | b | b | C22b
| When to Choose a Program (in-depth) |  |  | t | b |  | C22b |  | t | b |  | C22a
| Program Organization (in-depth) |  |  | t | b |  | C22d |  | t | b | b | C22c
| Multi-Organization Programs (in-depth) |  |  | b |  |  | C22e |  | b | b |  | C22d
| Benefits Management (in-depth) |  |  | b |  |  | C12a |  | t | b |  | C12a
| Program Lifecycle (in-depth) |  |  | b |  |  | C22f |  | b | b |  | C22e
| Core Documents (in-depth) |  |  | b |  |  | C22g |  | b | b |  | C22f | Benefit realization plan added as a core document
9.03 | Portfolio Management
| Portfolio Management |  |  | b | b | b | C23a |  | t | t | b | C23a | Management by projects defined separately
| Multi-Project Management |  |  | b | b | b | C23a |  | t | t | b | C23a
| Differences Between Program, Portfolio, and Multi-Project Management |  |  | b | b | b | C23a |  | t | t | b | C23a
| Developing a Portfolio Annual Plan (Advanced) |  |  | t | b |  | C23c |  | a | t |  | C23c | Bell diagram removed as a technique
| Portfolio Organization (Advanced) |  |  | t | b |  | C23b |  | t | b | b | C23b
| Portfolio Process (Advanced) |  |  | t | b |  | C23d |  | t | b |  | C23d
9.04 | Support Functions and Setting Up a PPP Organization
| PMO Characteristics |  |  | t | b |  | C24a |  | t | b | b | C24c
| PMO Service Portfolio |  |  | t | b |  | C24a |  | t | b | b | C24c
| Added Value of PMO ● |  |  | t | b
| PMO Value Added |  |  | t | b |  | C24b |  | t | b | b | C24d | PMO value matrix removed
| PM standards: PMBoK, PRINCE2, PMW, PMC |  |  | n | b
| Setting Up a PPP Organization (Advanced) |  |  | t |  |  | C24c |  | a | b |  | C24a | Content updated
|  | > Setting Up a Permanent PMO | [6 empty] | t | b |  | C24b | Obsolete but still an IPMA PMO learning outcome
| Project Management Standards (Advanced) |  |  | b |  |  | C26b |  | t | b |  | C26b | PM2 added; PRINCE2 and PMBOK updated to 7th edition / PM2 is not a final requirement for IPMA PMO
|  | > Project-Based Working and Project-BasedCreation | [6 empty] | t | b |  | C26b | PMW and PMC have been discontinued; still a final term for IPMA PMO
| ISO 21502:2020, Guidelines for PM (Advanced) |  |  | b |  |  | C26a |  | b |  |  | C26a | Content updated to ISO 2020 version
| IPMA Organizational Competence Baseline (Advanced) | [7 empty] | t |  |  | C24e
| Identifying the Maturity Level (Advanced) | [7 empty] | t |  |  | C24e
9.05 | Process Development Methods
| Agile |  |  | a | t | b | C27a |  | t | t | b | C27a
| Agile in day-to-day operations and in projects |  |  | a | t | b | C27a |  | t | t | b | C27a | New, adapted from the EN book
| Scrum |  |  | t | t | b | C27b |  | t | t | b | C27b | Scrum Guide 2020
| Scrum in Projects |  |  | t | t | b | C27b |  | t | t | b | C27b | New, adapted from the EN book
| Lean Six Sigma (Advanced) |  |  | b | b |  | C27c |  | b | b |  | C27c | Principles updated
| Kanban (Advanced) |  |  | t | t | b | C27d |  | t | b | b | C27d | Principles updated
10.00 | Internal Context
10.01 | Organizational Theory
| Permanent Organization |  |  | a | t | b | C25a |  | b | b | b | C25a | Definition of “span of control” updated
| > Flat versus hierarchical organization |  |  | a | t | b | C25c |  | b | b |  | C25c
| Interfaces between project-based and permanent organizations |  |  | a | t | b | C25e |  | b | b | b | C25e | Content updated
| Organizational Models |  |  | a | t | b | C25e |  | b | b | b | C25e | Functional project structure instead of project coordination structure
| Systems Approach (Advanced) |  |  | a | t |  | C25f |  | t | b |  | C25f | Content updated
| Organizational Configurations (Advanced) |  |  | t | b |  | C25b |  | b |  |  | C25b
| Total Quality Management (Advanced) |  |  | b |  |  | C25g |  | b |  |  | C25g | Content updated
| Theory of Constraints (Advanced) |  |  | t |  |  | C25h | [5 empty] | New, taken from the EN book; incorrect section title!
10.02 | Human Resources Management
| Personnel Policy and Management |  |  | b | b |  | C28a |  | t | b | b | C28a
| Human Resources Management in Projects |  |  | b | b |  | C28a |  | t | b | b | C28a
| Knowledge Management (Advanced) |  |  | t | b |  | C28c | [5 empty] | New, adapted from the EN book
| Competency Management (Advanced) |  |  | t | b |  | C28b |  | t | b |  | C28b
Single, dual, and triple learning (advanced)
10.03 | Financial Administration
| Cost Classification |  |  | b | b | b | C29a |  | b | b | b | C29a
| Fundamentals of Financial Accounting (Advanced) |  |  | b | b |  | C29c |  | b | b |  | C29c
| Accounting Records (Advanced) |  |  | b | b |  | C29c |  | b | b |  | C29c
| Financial Statements (Advanced) |  |  | t | b |  | C29d |  | b | b |  | C29d
|  | > OPEX and CAPEX |  | b | b |  | C29e |  | b | b |  | C29e
|  | > Investments and Depreciation |  | b | b |  | C29e |  | b | b |  | C29e
|  | > Financial Ratios | [10 empty] | New, taken from the English book; no Dutch learning outcome
| Calculation of Net Cash Flow (Advanced) | [7 empty] | b | b |  | C29f |  | ?
| Project Valuation (Advanced) |  |  | t | b |  | C29f |  | b | b |  | C29g |  | ?
| Allocation of Indirect Costs (Advanced) |  |  | b | b |  | C29b |  | b |  |  | C29b
11.00 | External Context
11.01 | Health, Safety, Security, and Environment
| Occupational Health and Safety Legislation |  |  | t | b | b | C33a |  | t | b | b | C33a
| Occupational Health and Safety Legislation in the Netherlands |  |  | t | b | b | C33a |  | t | b | b | C33a
| (Data) Security |  |  | t | b | b | C33c,d |  | t | t | b | C33c | NIS2 Directive included in the explanatory notes
| General Data Protection Regulation |  |  | t | b | b | C33c |  | t | t | b | C33c | Legal bases listed separately
| Environmental Legislation |  |  | b | b |  | C33b |  | b | b |  | C33b
| Environmental Act in the Netherlands |  |  | b | b |  | C33b |  | b | b |  | C33b | Environmental Act instead of Environmental Management Act
11.02 | Sustainability
| Sustainable Development |  |  | a | t | b | C31a |  | t | t | b | C31a
| People, Planet, Profit Principle (3P Principle) |  |  | b | b | b | C31a |  | t | t | b | C31a
| Sustainable Development in Projects |  |  | t | b | b | C31b |  | a | t | b | C31c | New: elaboration on sustainable development
| Corporate Social Responsibility |  |  | t | b | b | C31b |  | a | t | b | C31c
| The Triple Bottom Line (TBL) |  |  | a | t | b | C31a | [5 empty] | New: Reporting on the 3P principles
| The 10 Principles of the UN Global Compact (Advanced) | [7 empty] | t | b |  | C31b
| ISO 26000:2010 CSR (in-depth) |  |  | b |  |  | C31c |  | a | t | b | C31c
11.03 | Laws and Regulations
| Agreements |  |  | a | t | b | C32c |  | t | b | b | C32d | Defects of consent added
| Breach of Contract |  |  | a | t | b | C32d |  | t | b | b | C32e
| Unlawful Conduct and Tort |  |  | b | b | b | C32e |  | t | b | b | C32f | Content updated
| Regulatory Authorities |  |  | b | b |  | C32h | [5 empty] | New, adapted from the EN book
| Functional liability |  |  | t | b | b | C32b |  | b | b | b | C32c
| Areas of Law (in-depth) |  |  | b | b |  | C32a |  | b | b |  | C32b
| Intellectual Property Law (Advanced) |  |  | b | b |  | C32g |  | b | b |  | C32h | Content updated
| Mandatory, Regulatory, and Supplementary Law (in-depth) |  |  | b | b |  | C32a |  | b | b |  | C32b | Content updated
| Sources of Law (in-depth) | [7 empty] | b | b |  | C32a
11.04 | Influence and Interests
| Projects Related to Influence and Interests |  |  | b | b | b | C41a |  | t | t | b | C41a | New, included as an introduction to the following learning outcomes
| Power and Authority |  |  | b | b | b | C41a |  | t | b | b | C41d | Classification based on Max Weber removed; concept of authority added
| Principles of influence |  |  | t | t | b | C41b |  | t | t | b | C41a | Principle of unity added, in accordance with Cialdini’s 2021 update
| PESTLE analysis |  |  | a | t | b | C41d |  | t | b | b | C41d
| Sources of Interests (Advanced) |  |  | a | b |  | C41c |  | t | b |  | C41b
| Competitive and Comparative Advantages (Advanced) | [7 empty] | t | b |  | C41b
| Conflicts of Interest (in-depth) | [7 empty] | t | b |  | C41c | Removed; see Chapter 8.07 (G72d)
11.05 | Culture and Values
| Projects and Culture and Values |  |  | t | t | b | C51a | [5 empty] | New, included as an introduction to the following learning outcomes
| Dimensions of National Cultures |  |  | a | t | b | C51b |  | t | t | b | C51a | Content updated
| Organizational Culture Model |  |  | b | b | b | C51d |  | b | b |  | C51c
| Organizational Culture and Decision-Making (Advanced) |  |  | b |  |  | C51c |  | b | b |  | C51b
| Management in Different Cultures (in-depth) |  |  | b |  |  | C51c |  | b | b |  | C51b

## Learning Objectives
Reference Table: Learning Objectives for IPMA PM and IPMA PMO for IPMA Certification
Based on the new PMO learning outcomes effective July 1, 2026
ID | Topic |  | IPMA PM |  |  |  | IPMA PMO
|  |  | B | C | D | Terminology | B | C | D | Terminology
[6 empty] | terms |  |  |  | terms
Technical Competencies
3.00 | Project orientation
| What is a project? |  | ● | ● | ● | C21a | ● | ● | ● | C21a
| What is project management? |  | ● | ● | ● | C21b | ● | ● | ● | C21b
| Reasons to Start a Project |  | ● | ● | ● | C21f | ● | ● | ● | C21f
| Projects in Organizations |  | ● | ● | ● | C21c | ● | ● | ● | C21c
| Characteristics of a project |  | ● | ● | ● | C21e | ● | ● | ● | C21e
| Conditions of a project |  | ● | ● | ● | C21e | ● | ● | ● | C21e
| Work Methods |  | ● | ● | ● | C21d | ● | ● | ● | C21d
| Phasing, managing, and decision-making |  | ● | ● | ● | C21h | ● | ● | ● | C21h
| Triple Constraint |  | ● | ● | ● | V11a | ● | ● | ● | V11a
| Projects within the product lifecycle |  | ● | ● | ● | C21g | ● | ● | ● | C21g
| Projects at Different Levels |  | ● | ● | ● | C21i | ● | ● | ● | C21i
| Project results, outcomes, benefits, and objectives |  | ● | ● | ● | V21a | ● | ● | ● | V21a
| Customization |  | ● | ● | ● | C27a | ● | ● | ● | C27a
| Project Excellence Baseline (in-depth) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
4.00 | Project preparation
4.01 | Project preparation phase
| Project preparation phase |  | ● | ● | ● | V101a | ● | ● | ● | V101a
| Project mandate and project proposal |  | ● | ● | ● | V101a | ● | ● | ● | V101a
| Project Assignment |  | ● | ● | ● | V101b | ● | ● | ● | V101b
| Project Definition Phase Plan |  | ● | ● | ● | V101c | ● | ● | ● | V101c
| Project Decision |  | ● | ● | ● | V101c | ● | ● | ● | V101c
4.02 | Stakeholders
| Stakeholder Management |  | ● | ● | ● | V121b | ● | ● | ● | V121b
| Stakeholder Analysis |  | ● | ● | ● | V121a | ● | ● | ● | V121a
| Stakeholder Management Strategy |  | ● | ● | ● | V121b | ● | ● | ● | V121b
| Communication Plan |  | ● | ● | ● | V121b | ● | ● | ● | V121b
| Stakeholder Engagement |  | ● | ● | ● | V121c | ● | ● | ● | V121c
| Managing Expectations |  | ● | ● | ● | V121c | ● | ● | ● | V121c
4.03 | Project Organization
| Project Governance |  | ● | ● | ● | V51a | ● | ● | ● | V51a
| Principles of Project Organization |  | ● | ● | ● | V51bc | ● | ● | ● | V51bc
| Project Management Structure |  | ● | ● | ● | V51d | ● | ● | ● | V51d
| Project Organization |  | ● | ● | ● | V51d | ● | ● | ● | V51d
| Roles and Responsibilities |  | ● | ● | ● | V51e | ● | ● | ● | V51e
| Consultation Structure and the Linking-Pin Principle |  | ● | ● | ● | V51f | ● | ● | ● | V51f
| Responsibility Matrix |  | ● | ● | ● | V51g | ● | ● | ● | V51g
4.04 | Requirements and Objectives
| Project Results, Objectives, Outcomes, Benefits, and Goals |  | ● | ● | ● | V21a | ● | ● | ● | V21a
| Expectations, requirements, and acceptance criteria |  | ● | ● | ● | V21d | ● | ● | ● | V21d
| Quality Requirements and Specifications |  | ● | ● | ● | V21ef | ● | ● | ● | V21ef
| Value Management (in-depth) |  | ● | ● | ○ | V21b | ● | ● | ○ | V21b
| Total Cost of Ownership (in-depth) |  | ● | ● | ○ | V21c | ● | ● | ○ | V21c
| Product Cost Management (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
4.05 | Risks and Opportunities
| Risks and Opportunities |  | ● | ● | ● | V111cg | ● | ● | ● | V111ce
| Various risk concepts |  | ● | ● | ● | V111d | ● | ● | ● | V111c
| Risk Management |  | ● | ● | ● | V111b | ● | ● | ● | V111b
| Risk Management Strategy |  | ● | ● | ● | V111a | ● | ● | ● | V111a
| Risk owner and risk action owner |  | ● | ● | ● | V111e | ● | ● | ● | V111d
| Types of Risks |  | ● | ● | ○ | V111h | ● | ● | ● | V111f
| Risk Categories |  | ● | ● | ● | V111i | ● | ● | ● | V111f
| Risk Mitigation Measures |  | ● | ● | ● | V112b | ● | ● | ● | V112b
| Inherent, residual, and secondary risk |  | ● | ● | ● | V112d | ● | ● | ● | V112d
| Risk techniques, risk register |  | ● | ● | ● | V113a | ● | ● | ● | V113a
| Risk budget and contingency reserve |  | ● | ● | ● | V113d | ● | ● | ● | V113d
| Probability Measures (Advanced) |  | ● | ● | ○ | V112c | ● | ● | ○ | V112c
| ISO 31000:2018: Risk Management (Advanced) |  | ● | ● | ○ | V112a | ● | ● | ○ | V112a
| Risk Identification Techniques (Advanced) |  | ● | ● | ○ | V113b | ● | ● | ○ | v113b
| Risk Analysis Techniques (Advanced) |  | ● | ● | ○ | V113c | ● | ● | ○ | V113c
ID | Topic |  | IPMA PM |  |  |  | IPMA PMO
|  |  | B | C | D | Terminology | B | C | D | Terminology
[6 empty] | terms |  |  |  | terms
5.00 | Project Definition
5.01 | Project Definition Phase
| Activities in the project definition phase |  | ● | ● | ● | V102b | ● | ● | ● | V102b
| Project Management Plan |  | ● | ● | ● | V102b | ● | ● | ● | V102b
| Project Start-up |  | ● | ● | ● | V102a | ● | ● | ● | V102a
| Kick-off |  | ● | ● | ● | V102a | ● | ● | ● | V102a
| Project evaluation and decision |  | ● | ● | ● | V102d | ● | ● | ● | V102d
| Setting Up Project Support (Advanced) |  | ● | ● | ○ | V102c | ● | ● | ● | V102c
5.02 | Project Design
| Project Approach and Project Design |  | ● | ● | ● | V11b | ● | ● | ● | V11b
| Project Success |  | ● | ● | ● | V11c | ● | ● | ● | V11c
| Project Success Criteria |  | ● | ● | ● | V11a | ● | ● | ● | V11a
| Project Success Factors |  | ● | ● | ● | V11b | ● | ● | ● | V11b
| Project Management Success |  | ● | ● | ● | V11c | ● | ● | ● | V11c
| Lessons Learned |  | ● | ● | ● | V11e | ● | ● | ● | V11e
| Diamond Model (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Project Performance Management (Advanced) |  | ● | ● | ○ | V11d | ● | ● | ○ | V11d
5.03 | Scope
| Scope |  | ● | ● | ● | V31a | ● | ● | ● | V31a
| Scope Creep and Scope Changes |  | ● | ● | ● | V31b | ● | ● | ● | V31b
| Project Decomposition |  | ● | ● | ● | V32a | ● | ● | ● | V32a
| Work Breakdown Structure (WBS) |  | ● | ● | ● | V32b | ● | ● | ● | V32b
| Product Breakdown Structure (PBS) |  | ● | ● | ● | V32c | ● | ● | ● | V32c
| Scope (Configuration) Management |  | ● | ● | ● | V31a | ● | ● | ● | V31a
| Position of Subprojects in a WBS (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
5.04 | Quality
| Process and Product Quality |  | ● | ● | ● | V61a | ● | ● | ● | V61a
| Standard operating procedures |  | ● | ● | ○ | V61b | ● | ● | ○ | V61b
| Verification and validation |  | ● | ● | ● | V61c | ● | ● | ● | V61c
| Quality Management |  | ● | ● | ● | V61d | ● | ● | ● | V61d
| Quality Management Strategy and Plan |  | ● | ● | ● | V61e | ● | ● | ● | V61e
| Deming Cycle |  | ● | ● | ● | V104g | ● | ● | ● | V104g
| Standards, norms, and regulations |  | ● | ● | ● | C32f | ● | ● | ● | C32f
| Quality review, audit, and evaluation |  | ● | ● | ● | V62a | ● | ● | ● | V62a
| Quality Register/Test Register |  | ● | ● | ● | V62d | ● | ● | ● | V62d
| Quality Tools |  | ● | ● | ● | V61f | ● | ● | ● | V61f
| Additional Quality Tools (Advanced) |  | ● | ● | ○ | V61g | ● | ● | ○ | V61g
| Inspection Methods and Techniques (Advanced) |  | ● | ● | ○ | V62b | ● | ● | ○ | V62b
| Test Concepts and Methods (Advanced) |  | ● | ● | ○ | V62c | ● | ● | ○ | V62c
| Quality Costs (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
5.05 | Time
| Planning levels |  | ● | ● | ● | V41a | ● | ● | ● | V41a
| Baselines |  | ● | ● | ● | V41b | ● | ● | ● | V41b
| Milestones, Phases, and Decision Points |  | ● | ● | ● | V41f | ● | ● | ● | V41f
| Phasing Models |  | ● | ● | ● | V41g | ● | ● | ● | V41g
| Planning Techniques |  | ● | ● | ○ | V41d | ● | ● | ○ | V41d
| Precedence chart |  | ● | ● | ○ | V41d | ● | ● | ○ | V41d
| Gantt chart |  | ● | ● | ● | V41c | ● | ● | ● | V41c
| Shortening the Timeline |  | ● | ● | ● | V41h | ● | ● | ● | V41h
| Other planning constraints (in-depth) |  | ● | ● | ○ | V41e | ● | ● | ○ | V41e
| Uncertainty Analysis |  | ● | ● | ○ | V103c | ● | ● | ○ | V103c
5.06 | People and Resources
| Capacity Management |  | ● | ● | ● | V81a | ● | ● | ● | V81a
| Gross-Net Capacity |  | ● | ● | ● | V103a | ● | ● | ● | V103a
| Capacity Plan |  | ● | ● | ● | V81bc | ● | ● | ● | V81bc
| Estimation methods and techniques |  | ● | ● | ● | V103b | ● | ● | ● | V103b
| Critical Chain Method (in-depth) |  | ● | ● | ○ | V81d | ● | ● | ○ | V81d
5.07 | Finance
| Estimating, Budgeting, and Monitoring |  | ● | ● | ● | V72c | ● | ● | ● | V72c
| Cost Breakdown |  | ● | ● | ● | V71a | ● | ● | ● | V71a
| Reserves |  | ● | ● | ● | V71c | ● | ● | ● | V71c
| Cost and Budget Monitoring |  | ● | ● | ● | V72e | ● | ● | ● | V72e
| Reporting Standards |  | ● | ● | ● | V72d | ● | ● | ● | V72d
| Alignment of project and general accounting |  | ● | ● | ● | V72b | ● | ● | ● | V72b
| Power of attorney and proxy |  | ● | ● | ● | V72a | ● | ● | ● | V72a
ID | Topic |  | IPMA PM |  |  |  | IPMA PMO
|  |  | B | C | D | Terminology | B | C | D | Terminology
[6 empty] | terms |  |  |  | terms
| Linking CBS with WBS and OBS (advanced) |  | ● | ● | ● | V71b | ● | ● | ● | V71b
| Liquidity Planning (Advanced) |  | ● | ● | ○ | V73b | ● | ● | ● | V73b
| Project Financing (Advanced) |  | ● | ○ | ○ | V73a | ● | ● | ○ | V73a
| Liability Accounting (Addendum) |  | ○ | ○ | ○ | ○ | ● | ● | ● | V72f
5.08 | Business Justification
| Characteristics of a business case |  | ● | ● | ● | C14a | ● | ● | ● | C14a
| Business case document |  | ● | ● | ● | C14a | ● | ● | ● | C14a
| Baseline measurement, baseline and base scenarios, and delta measurement |  | ● | ● | ● | C14b | ● | ● | ● | C14b
| Business case in the product life cycle |  | ● | ● | ● | C14de | ● | ● | ● | C14de
| Client and contractor business cases |  | ● | ● | ● | C14c | ● | ● | ● | C14c
6.00 | Project implementation and closure
6.01 | Procurement
| Make or buy |  | ● | ● | ● | V91a | ● | ● | ● | V91a
| Procurement process |  | ● | ● | ● | V91c | ● | ● | ● | V91c
| Selection and Award Criteria |  | ● | ● | ● | V91c | ● | ● | ● | V91c
| Best-Efforts and Results-Based Obligations |  | ● | ● | ● | V92c | ● | ● | ● | V92c
| Standard Contract Clauses |  | ● | ● | ● | V92b | ● | ● | ● | V92b
| General Terms and Conditions |  | ● | ● | ● | V92b | ● | ● | ● | V92b
| Responsibilities |  | ● | ● | ● | V91c | ● | ● | ● | V91c
| Organizational Procurement Strategy (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Supplier Development (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Procurement Strategy and Plan (Advanced) |  | ● | ● | ○ | V91b | ● | ● | ○ | V91b
| Types of Contracts (in-depth) |  | ● | ● | ○ | V92a | ● | ● | ○ | V92a
| RFI, RFS, RFP, RFQ (Advanced) |  | ● | ● | ○ | V91d | ● | ● | ○ | V91d
| Concept of Supply and Demand (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Bidding Procedures (Advanced) |  | ● | ● | ○ | V91h | ● | ● | ○ | V91h
| Pre-Contractual Agreements (Advanced) |  | ● | ● | ○ | V91e | ● | ● | ○ | V91e
| Financial Guarantees (Advanced) |  | ● | ● | ○ | V92d | ● | ● | ○ | V92d
| European procurement (in-depth) |  | ● | ● | ● | V91g | ● | ● | ○ | V91g
| Contract Management (Advanced) |  | ● | ● | ○ | V92e | ● | ● | ○ | V92e
| Claims Management (Advanced) |  | ● | ● | ○ | V92f | ● | ● | ○ | V92f
| Partnerships (Advanced) |  | ● | ○ | ○ | V91f | ● | ○ | ○ | V91f
| Supply Chain Management (Advanced) |  | ● | ● | ○ | C25d | ● | ○ | ○ | C25d
6.02 | Change Management
| Change Management vs. Change Leadership |  | ● | ● | ● | V105a | ● | ● | ● | V105a
| Changes and Project Issues |  | ● | ● | ● | V105b | ● | ● | ● | V105b
| Change Strategy and Procedure |  | ● | ● | ● | V105c | ● | ● | ● | V105c
| Deviations from Specifications |  | ● | ● | ● | V105b | ● | ● | ● | V105b
| Other Project Issues |  | ● | ● | ● | V105b | ● | ● | ● | V105b
| Issue Register |  | ● | ● | ● | V105c | ● | ● | ● | V105c
| Change Authority |  | ● | ● | ● | V105d | ● | ● | ● | V105d
| Change Budget |  | ● | ● | ● | V105d | ● | ● | ● | V105d
| Priority and urgency |  | ● | ● | ● | V105e | ● | ● | ● | V105e
| Configuration Management (Advanced) |  | ● | ● | ○ | V33a-d | ● | ● | ● | V33a-d
6.03 | Information and Documentation
| Information vs. Data |  | ● | ● | ● | V52b | ● | ● | ● | V52b
| Information and Document Management |  | ● | ● | ● | V52c | ● | ● | ● | V52c
| Information Management Strategy |  | ● | ● | ● | V52a | ● | ● | ● | V52a
| Information Management Plan |  | ● | ● | ● | V52f | ● | ● | ● | V52f
| Information Management Infrastructure |  | ● | ● | ● | V52d | ● | ● | ● | V52d
| Quality and Security Requirements |  | ● | ● | ● | V52g | ● | ● | ● | V52g
| Project File Structure |  | ● | ● | ● | V52h | ● | ● | ● | V52h
| I/O matrix |  | ● | ● | ○ | V52e | ● | ● | ○ | V52e
| Information Management Techniques (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
6.04 | Control and Reporting
| Management Cycle |  | ● | ● | ● | V104g | ● | ● | ● | V104g
| Management and Reporting Levels |  | ● | ● | ● | V104h | ● | ● | ● | V104h
| Management by Objectives |  | ● | ● | ● | V104a | ● | ● | ● | V104a
| Management by Exception |  | ● | ● | ● | V104b | ● | ● | ● | V104b
| Day-to-day management |  | ● | ● | ● | V104c | ● | ● | ● | V104c
| Managing Phase Transitions |  | ● | ● | ● | V104d | ● | ● | ● | V104d
| Escalating Deviations |  | ● | ● | ● | V104e | ● | ● | ● | V104e
| Project Control |  | ● | ● | ● | V104f | ● | ● | ● | V104f
| Project management products |  | ● | ● | ● | V104fk | ● | ● | ● | V104fk
| Trend Analyses |  | ● | ● | ● | V104j | ● | ● | ● | V104j
| Earned Value Analysis (Advanced) |  | ● | ● | ○ | V104i | ● | ● | ○ | V104i
ID | Topic |  | IPMA PM |  |  |  | IPMA PMO
|  |  | B | C | D | Terminology | B | C | D | Terminology
[6 empty] | terms |  |  |  | terms
6.05 | Change and Transformation
| Change Management |  | ● | ● | ● | V131a | ● | ● | ● | V131a
| Change Management Approach |  | ● | ● | ● | V131b | ● | ● | ● | V131b
| Leadership in Change – Kotter |  | ● | ● | ○ | V131c | ● | ● | ○ | V131c
| Kübler-Ross Stages of Grief (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Diffusion of Innovations – Rogers (Advanced) |  | ● | ● | ○ | V131d | ● | ○ | ○ | V131d
| Learning Organizations – Senge (Advanced) |  | ● | ● | ○ | V131e | ● | ● | ○ | V131e
| Transformational Learning – Schein (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Change Paradigms - De Caluwé/Vermaak |  | t |  |  |  | ● | ● | ●
6.06 | Project Closure
| Delivery and Handover of Project Results |  | ● | ● | ● | V106a | ● | ● | ● | V106a
| Winding Down the Project |  | ● | ● | ● | V106b | ● | ● | ● | V106b
| Evaluation |  | ● | ● | ● | V106c | ● | ● | ● | V106c
| Dissolving the Project Team |  | ● | ● | ● | V106b | ● | ● | ● | V106b
| Closure and Discharge |  | ● | ● | ● | V106d | ● | ● | ● | V106d
Behavioral Competencies
7.00 | Self-Management
7.01 | Self-Reflection and Self-Management
| Self-Reflection and Self-Analysis |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Emotional Intelligence |  | ● | ● | ● | G11a | ● | ● | ● | G11a
| Johari Window |  | ● | ● | ● | G11c | ● | ● | ● | G11c
| Big Five personality theory |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Core Quadrants |  | ● | ● | ● | G11d | ● | ● | ● | G11d
| Personal Effectiveness |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Self-Motivation |  | ● | ● | ● | G12a | ● | ● | ● | G12a
| The Seven Habits of Highly Effective Leaders |  | ● | ● | ○ | G12c | ● | ● | ○ | G12c
| Personal Time Management |  | ● | ● | ● | G12d | ● | ● | ● | G12d
| Stress Management |  | ● | ● | ● | G13a | ● | ● | ● | G13a
| Tension versus Stress (Eustress and Distress) |  | ● | ● | ● | G13a | ● | ● | ● | G13a
| Triggers and symptoms of stress |  | ● | ● | ● | G13b | ● | ● | ● | G13b
| Stress Reduction Techniques |  | ● | ● | ● | G13c | ● | ● | ● | G13c
| Rational Emotive Therapy (in-depth) |  | ● | ● | ○ | G11b | ● | ○ | ○ | G11b
| Personal Time Management Techniques (in-depth) |  | ● | ● | ○ | G12e | ● | ● | ○ | G12e
| Steps in Goal Setting (Advanced) |  | ● | ● | ○ | G12b | ● | ● | ○ | G12b
| Intervention Techniques for Reducing Stress (in-depth) |  | ● | ● | ○ | G13d | ● | ● | ○ | G13d
7.02 | Personal Integrity and Reliability
| Aspects of Reliability |  | ● | ● | ● | G22a | ● | ● | ● | G22a
| Types of Ethics |  | ● | ● | ● | G21a | ● | ● | ● | G21a
| Principles of Social Justice and Sustainability |  | ● | ● | ○ | G21b | ● | ● | ○ | G21b
| Professional Standards and the IPMA Code of Conduct |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Ethics Test (Advanced) |  | ● | ● | ○ | G21c | ● | ● | ○ | G21c
| Personal Ethics vs. Business Ethics (Advanced) |  | ● | ● | ○ | G21c | ● | ● | ○ | G21c
| UN Universal Declaration of Human Rights (in-depth) |  | ● | ● | ○ | G22c | ● | ● | ○ | G22c
7.03 | Personal Communication
| Communication |  | ● | ● | ● | G31acde | ● | ● | ● | G31acde
|  | > Verbal and nonverbal communication | ● | ● | ● | G32a | ● | ● | ● | G32a
| Aspects of Communication |  | ● | ● | ● | G31b | ● | ● | ● | G31b
| Active Listening |  | ● | ● | ● | G32b | ● | ● | ● | G32b
| Asking the Right Questions |  | ● | ● | ● | G32c | ● | ● | ● | G32c
| Giving and Receiving Feedback |  | ● | ● | ● | G32d | ● | ● | ● | G32d
| Meetings |  | ● | ● | ● | G33abc | ● | ● | ● | G33abc
| Facilitated workshops |  | ● | ● | ● | G34abc | ● | ● | ● | G34abc
| Written communication |  | ● | ● | ● | G36ab | ● | ● | ● | G36ab
| Presentations |  | ● | ● | ● | G35ac | ● | ● | ● | G35ac
| Elevator pitch (in-depth) |  | ● | ● | ○ | G35b | ● | ● | ○ | G35b
| Delivering Bad News (Advanced) |  | ● | ○ | ○ | G32e | ● | ○ | ○ | G32e
8.00 | Connecting with Others
8.01 | Relationships and Engagement
| Aspects, characteristics, and policies regarding openness |  | ● | ● | ● | G41b | ● | ● | ● | G41b
| Building Arguments |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Building Networks |  | ● | ● | ○ | G22b | ● | ● | ○ | G22b
| Motivation Theories |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Maslow’s Hierarchy of Needs |  | ● | ● | ● | G43b | ● | ● | ● | G43b
| Motivation and Hygiene Factors |  | ● | ● | ○ | G43a | ● | ● | ○ | G43a
| Theory X and Theory Y managers |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Creating an Open Corporate Culture (Advanced) |  | ● | ○ | ○ | G41a | ● | ○ | ○ | G41a
| Behavioral Patterns/Leary’s Rose (in-depth) |  | ● | ● | ○ | G42b | ● | ● | ○ | G42c
| The Project Manager as an Advisor (in-depth) |  | ● | ● | ○ | G42a | ● | ● | ○ | G42a
ID | Topic |  | IPMA PM |  |  |  | IPMA PMO
|  |  | B | C | D | Terminology | B | C | D | Terminology
[6 empty] | terms |  |  |  | terms
| Self-Determination Theory (in-depth) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Spiral Dynamics (in-depth) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
8.02 | Leadership
| Differences Between Leadership and Management |  | ● | ● | ● | G51a | ● | ● | ● | G51a
| Leadership Styles |  | ● | ● | ○ | G51d | ● | ● | ○ | G51d
| Contingency theory |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Situational Leadership |  | ● | ● | ● | G51c | ● | ● | ● | G51c
| Circles of Influence and Engagement |  | ● | ● | ● | G51e | ● | ● | ● | G51e
| Levels of Assertiveness |  | ● | ● | ● | G51f | ● | ● | ● | G51f
| Role content, interpretation, and expectations (in-depth) |  | ● | ● | ○ | G51g | ● | ● | ○ | G51g
| Coaching (in-depth) |  | ● | ○ | ○ | G51h | ● | ○ | ○ | G51h
| Servant leadership (in-depth) |  | ● | ○ | ○ | G51i | ● | ○ | ○ | G51i
| Meaning and Purpose (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Three Levels of Leadership (Advanced) |  | ● | ● | ○ | G51b | ● | ● | ○ | G51b
| Vroom and Yetton Decision-Making Model (Advanced) |  | ● | ○ | ○ | G51j | ● | ○ | ○ | G51j
8.03 | Teamwork
| Teams and Team Development Stages |  | ● | ● | ● | G61a | ● | ● | ● | G61a
| Situational Leadership and Team Development |  | ● | ● | ● | G61b | ● | ● | ● | G61b
| Interventions During Team Phase Transitions |  | ● | ● | ● | G61b | ● | ● | ● | G61b
| Team Building |  | ● | ● | ● | G61a | ● | ● | ● | G61a
| Dealing with Resistance |  | ● | ● | ● | G62c | ● | ● | ● | G62c
| Team Composition (Advanced) |  | ● | ● | ○ | G62a | ● | ● | ○ | G62a
| Developing an Effective Project Culture (Advanced) |  | ● | ● | ○ | G62f | ● | ● | ○ | G62f
| Team Roles (in-depth) |  | ● | ● | ○ | G62b | ● | ● | ○ | G62b
| Groupthink (in-depth) |  | ● | ● | ○ | G62d | ● | ○ | ○ | G62d
| Dealing with Resistance (Supplementary, In-Depth) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Remote Teams (Advanced) |  | ● | ● | ○ | G62e | ● | ● | ○ | G62e
8.04 | Resourcefulness
| Thinking Methods |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Analytical Problem Solving |  | ● | ● | ● | G81e | ● | ● | ● | G81e
| Creative Problem Solving |  | ● | ● | ● | G82a | ● | ● | ● | G82a
| Decision-making methods |  | ● | ● | ● | G81d | ● | ● | ● | G81d
| Cause Identification and Analysis Techniques |  | ● | ● | ○ | G81a | ● | ● | ○ | G81a
| Solution identification and analysis techniques |  | ● | ● | ○ | G81b | ● | ● | ○ | G81b
| Solution assessment and evaluation techniques |  | ● | ● | ○ | G81c | ● | ● | ○ | G81c
| Divergent creativity techniques |  | ● | ● | ● | G82b | ● | ● | ● | G82b
| Convergent creativity techniques |  | ● | ● | ● | G82d | ● | ● | ● | G82d
| Problem-Solving in Standardized Processes (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Additional Divergent Creativity Techniques (Advanced) |  | ● | ○ | ○ | G82c | ● | ○ | ○ | G82c
| Additional Convergent Creativity Techniques (Advanced) |  | ● | ○ | ○ | G82e | ● | ○ | ○ | G82e
| Structured Decision-Making Process (Advanced) |  | ● | ○ | ○ | G82f | ○ | ○ | ○ | ○
| Validating Products in Innovative Processes (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Implementation of Organizational Innovation (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
8.05 | Results-Orientation
| Efficiency, Effectiveness, and Productivity |  | ● | ● | ● | G101a | ● | ● | ● | G101a
| Continuous improvement (kaizen) |  | ● | ● | ○ | G101c | ● | ● | ● | G101c
| Techniques for improving efficiency (advanced) |  | ● | ● | ○ | G101d | ● | ● | ● | G101d
| Results-oriented project management (advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Political and Social Sensitivity (Advanced) |  | ● | ● | ○ | G101e | ● | ● | ○ | G101e
| Entrepreneurship (Advanced) |  | ● | ○ | ○ | G101b | ● | ○ | ○ | G101b
8.06 | Negotiation
| Negotiation strategies |  | ● | ● | ● | G91a | ● | ● | ● | G91a
| Positional negotiation |  | ● | ● | ● | G91c | ● | ● | ● | G91c
| Principled Negotiation – The Harvard Method |  | ● | ● | ● | G91b | ● | ● | ● | G91b
| Best Alternative Without a Contract (BAZO) |  | ● | ● | ● | G91b | ● | ● | ● | G91b
| Phases in a Negotiation Process (Advanced) |  | ● | ● | ○ | G91d | ● | ● | ○ | G91d
| Aspects of Influence in Negotiations (Advanced) |  | ● | ● | ○ | G91e | ● | ● | ○ | G91e
| Negotiation Tactics (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
8.07 | Conflicts and Crises
| Functional and Dysfunctional Conflicts |  | ● | ● | ● | G72b | ● | ● | ● | G72b
| Types of Conflicts |  | ● | ● | ○ | G72a | ● | ● | ○ | G72a
| Conflict Management Styles |  | ● | ● | ● | G72e | ● | ● | ● | G72e
| Stages of Conflict |  | ● | ● | ● | G72c | ● | ● | ● | G72c
| De-escalation in Different Stages of Conflict |  | ● | ● | ● | G72d | ● | ● | ● | G72d
| Different Roles in Conflicts (Advanced) |  | ● | ● | ○ | G72f | ● | ● | ○ | G72f
ID | Topic |  | IPMA PM |  |  |  | IPMA PMO
|  |  | B | C | D | Terminology | B | C | D | Terminology
[6 empty] | terms |  |  |  | terms
| Crises and Crisis Management (Advanced) |  | ● | ● | ○ | G71b | ● | ● | ○ | G71b
| Crisis Plan (Advanced) |  | ● | ○ | ○ | G71a | ● | ● | ○ | G71a
Contextual Competencies
9.00 | Implementing Change
9.01 | Strategy
| Company Mission, Vision, and Core Values |  | ● | ● | ● | C11ab | ● | ● | ● | C11ab
| Strategy and Strategic Goals |  | ● | ● | ● | C11f | ● | ● | ● | C11f
| Benchmarking |  | ● | ● | ● | C12c | ● | ● | ● | C12c
| SWOT Analysis |  | ● | ● | ● | C11e | ● | ● | ● | C11e
| 10 Ways to Develop Strategies (in-depth) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Business Model Canvas (in-depth) |  | ● | ● | ○ | C11d | ● | ○ | ○ | C11d
| McKinsey 7S Model (in-depth) |  | ● | ○ | ○ | C11c | ● | ○ | ○ | C11c
| Strategic Performance Management (Advanced) |  | ● | ● | ○ | C12b | ● | ● | ○ | C12b
| EFQM Model (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Investment Calculations (Advanced) |  | ● | ● | ● | C13a | ● | ● | ● | C13a
| Return on Investment (in-depth) |  | ● | ● | ● | C13a | ● | ● | ● | C13a
| Profitability Ratios (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Net Present Value (Advanced) |  | ● | ● | ○ | C13b | ● | ● | ○ | C13b
| Payback period (in-depth) |  | ● | ● | ○ | C13c | ● | ● | ○ | C13c
| Break-even point (in-depth) |  | ● | ● | ○ | C13c | ● | ● | ○ | C13c
9.02 | Program Management
| Programs and Program Management |  | ● | ● | ○ | C22a | ● | ● | ○ | C22a
| Differences Between Projects and Programs |  | ● | ● | ○ |  | ● | ● | ●
| Differences between projects and programs |  | ● | ● | ○ | C22c | ● | ● | ○ | C22c
| When to Choose a Program (in-depth) |  | ● | ● | ○ | C22b | ● | ● | ○ | C22b
| Program Organization (in-depth) |  | ● | ● | ○ | C22d | ● | ● | ○ | C22d
| Multi-Organization Programs (in-depth) |  | ● | ○ | ○ | C22e | ● | ○ | ○ | C22e
| Benefits Management (in-depth) |  | ● | ○ | ○ | C12a | ● | ○ | ○ | C12a
| Program Lifecycle (in-depth) |  | ● | ○ | ○ | C22f | ● | ● | ○ | C22f
| Core Documents (in-depth) |  | ● | ○ | ○ | C22g | ● | ● | ○ | C22g
9.03 | Portfolio Management
| Portfolio Management |  | ● | ● | ● | C23a | ● | ● | ● | C23a
| Multi-Project Management |  | ● | ● | ● | C23a | ● | ● | ● | C23a
| Differences Between Program, Portfolio, and Multi-Project Management |  | ● | ● | ● | C23a | ● | ● | ● | C23a
| Developing a Portfolio Annual Plan (Advanced) |  | ● | ● | ○ | C23c | ● | ● | ○ | C23c
| Portfolio Organization (Advanced) |  | ● | ● | ○ | C23b | ● | ● | ○ | C23b
| Portfolio Process (Advanced) |  | ● | ● | ○ | C23d | ● | ● | ○ | C23d
9.04 | Support Functions and Setting Up a PPP Organization
| PMO Characteristics |  | ● | ● | ○ | C24a | ● | ● | ● | C24a
| PMO Service Portfolio |  | ● | ● | ○ | C24b | ● | ● | ● | C24b
| Added Value of PMO ● |  | ● | ● | ○ |  | ● | ● | ●
| PMO Value Added |  | ● | ● | ○ | C24b | ● | ● | ● | C24b
| PM standards: PMBoK, PRINCE2, PMW, PMC |  | n | b
| Setting Up a PPP Organization (Advanced) |  | ● | ○ | ○ | C24c | ● | ● | ○ | C24c
| Project Management Standards (Advanced) |  | ● | ○ | ○ | C26b | ● | ○ | ○ | C26b
| ISO 21502:2020, Guidelines for PM (Advanced) |  | ● | ○ | ○ | C26a | ● | ○ | ○ | C26a
| IPMA Organizational Competence Baseline (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Identifying the Maturity Level (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
9.05 | Process Development Methods
| Agile |  | ● | ● | ● | C27a | ● | ● | ● | C27a
| Agile in day-to-day operations and in projects |  | ● | ● | ● | C27a | ● | ● | ● | C27a
| Scrum |  | ● | ● | ● | C27b | ● | ● | ● | C27b
| Scrum in Projects |  | ● | ● | ● | C27b | ● | ● | ● | C27b
| Lean Six Sigma (Advanced) |  | ● | ● | ○ | C27c | ● | ● | ○ | C27c
| Kanban (Advanced) |  | ● | ● | ● | C27d | ● | ● | ● | C27d
10.00 | Internal Context
10.01 | Organizational Theory
| Permanent Organization |  | ● | ● | ● | C25a | ● | ● | ● | C25a
|  | > Flat versushierarchical organization | ● | ● | ● | C25c | ● | ● | ○ | C25c
| Interfaces between project-based and permanent organizations |  | ● | ● | ● | C25e | ● | ● | ● | C25e
| Organizational Models |  | ● | ● | ● | C25e | ● | ● | ● | C25e
| Systems Approach (Advanced) |  | ● | ● | ○ | C25f | ● | ● | ○ | C25f
| Organizational Configurations (Advanced) |  | ● | ● | ○ | C25b | ● | ○ | ○ | C25b
| Total Quality Management (Advanced) |  | ● | ○ | ○ | C25g | ● | ○ | ○ | C25g
| Theory of Constraints (Advanced) |  | ● | ○ | ○ | C25h | ● | ○ | ○ | C25h
10.02 | Human Resources Management
| Personnel Policy and Management |  | ● | ● | ○ | C28a | ● | ● | ○ | C28a
| Human Resources Management in Projects |  | ● | ● | ○ | C28a | ● | ● | ○ | C28a
ID | Topic |  | IPMA PM |  |  |  | IPMA PMO
|  |  | B | C | D | Terminology | B | C | D | Terminology
[6 empty] | terms |  |  |  | terms
| Knowledge Management (Advanced) |  | ● | ● | ○ | C28c | ● | ● | ○ | C28c
| Competency Management (Advanced) |  | ● | ● | ○ | C28b | ● | ● | ○ | C28b
| Single, dual, and triple learning (advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
10.03 | Financial Administration
| Cost Classification |  | ● | ● | ● | C29a | ● | ● | ● | C29a
| Fundamentals of Financial Accounting (Advanced) |  | ● | ● | ○ | C29c | ● | ● | ○ | C29c
| Accounting Records (Advanced) |  | ● | ● | ○ | C29c | ● | ● | ○ | C29c
| Financial Statements (Advanced) |  | ● | ● | ○ | C29de | ● | ● | ○ | C29de
| Financial Ratios |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Calculation of Net Cash Flow (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| Project Valuation (Advanced) |  | ● | ● | ○ | C29f | ● | ● | ○ | C29f
| Allocation of Indirect Costs (Advanced) |  | ● | ● | ○ | C29b | ● | ● | ○ | C29b
11.00 | External Context
11.01 | Health, Safety, Security, and Environment
| Occupational Health and Safety Legislation |  | ● | ● | ● | C33a | ● | ● | ● | C33a
| (Data) Security |  | ● | ● | ● | C33c,d | ● | ● | ● | C33c,d
| General Data Protection Regulation |  | ● | ● | ● | C33c | ● | ● | ● | C33c
| Environmental Legislation |  | ● | ● | ○ | C33b | ● | ● | ○ | C33b
| Environmental Act in the Netherlands |  | ● | ● | ○ | C33b | ● | ● | ○ | C33b
11.02 | Sustainability
| Sustainable Development |  | ● | ● | ● | C31a | ● | ● | ● | C31a
| People, Planet, Profit Principle (3P Principle) |  | ● | ● | ● | C31a | ● | ● | ● | C31a
| Sustainable Development in Projects |  | ● | ● | ● | C31b | ● | ● | ● | C31b
| Corporate Social Responsibility |  | ● | ● | ● | C31b | ● | ○ | ○ | C31b
| The Triple Bottom Line (TBL) |  | ● | ● | ● | C31a | ● | ● | ● | C31a
| The 10 Principles of the UN Global Compact (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
| ISO 26000:2010 CSR (in-depth) |  | ● | ○ | ○ | C31c | ● | ○ | ○ | C31c
11.03 | Laws and Regulations
| Agreements |  | ● | ● | ● | C32c | ● | ● | ● | C32c
| Breach of Contract |  | ● | ● | ● | C32d | ● | ● | ● | C32d
| Unlawful Conduct and Tort |  | ● | ● | ● | C32e | ● | ● | ● | C32e
| Regulatory Authorities |  | ● | ● | ○ | C32h | ○ | ○ | ○ | ○
| Functional liability |  | ● | ● | ● | C32b | ● | ● | ● | C32b
| Areas of Law (in-depth) |  | ● | ● | ○ | C32a | ● | ● | ○ | C32a
| Intellectual Property Law (Advanced) |  | ● | ● | ○ | C32g | ● | ● | ○ | C32g
| Mandatory, Regulatory, and Supplementary Law (in-depth) |  | ● | ● | ○ | C32a | ● | ● | ○ | C32a
| Sources of Law (in-depth) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
11.04 | Influence and Interests
| Projects Related to Influence and Interests |  | ● | ● | ● | C41a | ● | ● | ● | C41a
| Power and Authority |  | ● | ● | ● | C41a | ● | ● | ● | C41a
| Principles of influence |  | ● | ● | ● | C41b | ● | ● | ● | C41b
| PESTLE analysis |  | ● | ● | ● | C41d | ● | ● | ● | C41d
| Sources of Interests (Advanced) |  | ● | ● | ○ | C41c | ● | ● | ○ | C41c
| Competitive and Comparative Advantages (Advanced) |  | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○
11.05 | Culture and Values
| Projects and Culture and Values |  | ● | ● | ● | C51a | ● | ● | ● | C51a
| Dimensions of National Cultures |  | ● | ● | ● | C51b | ● | ● | ● | C51a
| Organizational Culture Model |  | ● | ● | ● | C51d | ● | ● | ○ | C51c
| Organizational Culture and Decision-Making (Advanced) |  | ● | ○ | ○ | C51c | ● | ○ | ○ | C51b
| Management in Different Cultures (in-depth) |  | ● | ○ | ○ | C51c | ● | ○ | ○ | C51b
LEGEND
Certification Levels
B |  | IPMA-B
C |  | IPMA-C
D |  | IPMA-D
● |  | Applicable to the relevant certification level
○ |  | Not applicable to the relevant certification level
Final Objective |  | Coding in the IPMA Certification Exam Guide
Textbook
Column B |  | In the in-depth section of the IPMA textbook
Column C |  | Section in the IPMA textbook
Column D |  | Subsection in the IPMA textbook
Color coding
Competency Areas in the IPMA Textbook
Sections (4–11) in the IPMA textbook
Chapters in the IPMA textbook
A PMO learning outcome that is new as of July 1, 2026
A PMO learning outcome that will expire on July 1, 2026
Columns J-K-L, PMO greater than PM
Columns J-K-L, PMO less than PM
Addendum: IPMA PMO
One topic is missing from the IPMA textbook for the IPMA PMO certification .
5.07 |  | Obligation Tracking